## Plan Summary
TAC Digital Toolkit – Integration Implementation — Plan Summary (v2.1, 7 Sep 2026)
Planning anchor: integration platform and Priority 1 integrations ready for Claims Platform SIT. Hard date that does not move: Deloitte exit (Apr 27). Driving force: build new integrations for the DCP world, with intake governed by a thorough discovery process aligned to DCP needs. Existing IBM integrations are out of scope — most will not exist in the new world; IBM keeps running Avanti under an extended-support arrangement owned by another area (D29) until Avanti retires after DCP Release 1 (Nov 27, highly optimistic).
Three plan versions (reference-class adjusted)
Milestone | A — Anchor | B — Likely | C — Safe | Basis
Interim internet connectivity live (dev/test) | Oct 26 | Oct 26 | Nov 26 | Depends on IT Security approval of internet-based dev/test connectivity — start now.
MuleSoft platform ready (non-prod) | Nov 26 | Dec 26 | Jan 27 | +4 weeks for environment provisioning and security approvals (reference class: 4–8 weeks typical).
AWS enterprise connection operational (non-prod) | Jan 27 | Feb 27 | Feb 27 | External — AWS Tenancy Project (Arinco). Tracked as dependency D24.
Priority 1 integration build complete | Feb 27 | Mar 27 | Apr 27 | +4 weeks for legacy interface discovery (Avanti, eHealth, Westpac) — reference class 3–8 weeks.
AWS enterprise connection production-ready | Mid-Mar 27 | Late Mar 27 | Apr 27 | External — planning assumption is mid-March; escalate at first sign of slip.
Code complete / ready for production | Mar 27 | Apr 27 | May 27 | Cascades from build completion and enterprise connection.
Production deployment and hardening | Apr 27 | May 27 | Jun 27 | Requires production security approval — pre-approve approach in Q1 27.
Ready for Claims Platform SIT | End Apr 27 | End May 27 | End Jun 27 | A: 30–40% confidence. B: 60–70%. C: 85%. Present B as the realistic date; A only if every assumption holds.
Deloitte exit / capability transfer complete | Apr 27 | Apr 27 | Apr 27 | HARD — fixed contractual exit. Under B and C, TAC team completes production deployment without Deloitte on site. Confirm exact date.
IBM extended support in place (post Sep 27 end of life) | Sep 27 | — | — | EXTERNAL — another area's dependency (D29). No Digital Toolkit scope: legacy IBM integrations are not being migrated.
DCP Release 1 (Claims Platform go-live) | Nov 27 | — | — | EXTERNAL — Claims Platform programme; highly optimistic. Drives the intake pipeline: integrations are built for DCP needs, not migrated from IBM.
Critical path (Anchor plan)
1. | Security approval for internet-based dev/test (Sep–Oct 26)
2. | Interim internet connectivity live (Oct 26)
3. | Private Space + non-prod environments (Oct–Nov 26)
4. | Platform ready non-prod (Nov 26)
5. | P1 integration build (Nov 26–Feb 27)
6. | AWS enterprise connection non-prod (Jan 27) → migrate connectivity, pen test (Feb–Mar 27)
7. | AWS enterprise connection prod-ready (mid-Mar 27)
8. | Production build + security approval (Mar 27)
9. | Production deployment and hardening (Apr 27)
10. | Ready for Claims Platform SIT (end Apr 27)
What changed from the 4 Sep Keel extract
• | AWS workstream stripped back to an external dependency: Transit Gateway, VPC/subnet, CIDR allocation, route tables and Arinco onboarding moved to the AWS Tenancy Project. Digital Toolkit feeds requirements and tracks three AWS milestones.
• | Interim internet-based connectivity added as the unblocking path for platform enablement and build, with a later migration to the enterprise connection. Security approval for this is the first item on the critical path.
• | Governance milestones re-based to reality: Deloitte contract not yet executed (I9), so contract execution, kick-off and plan re-baseline now sit in Sep–Oct 26. Items whose window has passed are marked "Complete – confirm".
• | Reference-class buffers made explicit as their own rows (+4 weeks after platform ready and after P1 build) so the Likely dates are visible on the chart rather than hidden in estimates.
• | Payments / Westpac decision gate added from the 27 Aug pre-triage meeting: payment source of truth (Avanti vs Claims Platform) is a decision for Joshua Ly after Claims Platform discovery; P3 Payments build cannot start before it. eHealth push-to-pull agreement added as a decision gate for P2.
• | Scope position (corrected 7 Sep): migrating integrations off IBM is not a strategic direction and is out of scope — most legacy integrations will not exist in the DCP world. WP2 is re-framed around intake discovery aligned to DCP needs; new integrations are built from that funnel. Legacy IBM integrations run as-is under an extended-support arrangement owned by another area (D29) until Avanti retires. Anything legacy that surfaces will come via another transformation project through the intake process, not from this programme.
• | Assumptions section populated (was empty). Every date in the Anchor plan now has a named assumption behind it.
• | RAID: mitigations added for R19–R21; new risks R23–R28; new dependencies D26–D29; actions sheet added with owners and due dates.
• | Housekeeping to confirm: banner in the extract read "end September 2025" (should be 2026); "ARC and DRC approval" retained as written — confirm ARC is a real body or whether this should read DRC only.

## Programme Timeline
TAC Digital Toolkit – Integration Implementation — Programme Timeline v2.1 (re-planned 7 Sep 2026)
⚠ Hard date: Deloitte exit Apr 27. Legacy IBM integrations out of scope — run under extended support (other area, D29) until Avanti retires after DCP R1 (Nov 27, optimistic). Intake discovery aligned to DCP needs is the driving force. Original commitment: all MuleSoft environments live on M-POWER by end Sep 26 — treated as superseded, confirm. Legend: ◆ milestone · ◈ go-live/gate · Buffer = reference-class allowance
WP | ACTIVITY / STREAM | OWNER | STATUS | Apr 26 | May 26 | Jun 26 | Jul 26 | Aug 26 | ▶ Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 | Jul 27 | Aug 27 | Sep 27 | Oct 27 | Nov 27 | Dec 27 | Jan 28 | Feb 28 | Mar 28
M-POWER | M-POWER — TAC Azure Tenancy (external dependency)
M-POWER | TAC migration off WorkSafe shared tenancy | Neil Carroll | In progress | Separate workstream
M-POWER | Azure tenancy build | Neil Carroll | Complete – confirm | Azure build
M-POWER | Domain name cutover (unblocks platform enablement — D8) | Neil Carroll | Due this month | [5 empty] | ◆ Domain cutover
M-POWER | M-POWER production cutover — platform build can proceed (D1, D12) | Neil Carroll | Planned | [6 empty] | ◆ M-POWER GO
P-GX | P-GX — Project Governance
P-GX | Deloitte eServices contract executed (CEO submission — I9) | Paul Murray | At risk | [5 empty] | ◆ Contract
P-GX | MuleSoft licence procured (R16) | Trish Volante / Ankur Pawaria | At risk | [5 empty] | ◆ Licence
P-GX | Change Request approved — $290K to AWS Tenancy Project (I11) | Paul Murray / James Thomas | In flight | [5 empty] | ◆ CR
P-GX | Project kick-off — Deloitte squad mobilised, objectives confirmed | Paul Murray | Planned | [6 empty] | ◆ Kick-off
P-GX | Plan re-baselined (aligned to Claims Platform schedule) | Paul Murray | Planned | [6 empty] | ◆ Baseline
P-GX | Fortnightly reporting to business owner (AC20 cadence) | Paul Murray | Ongoing |  | Fortnightly reporting to business owner (AC20 cadence)
P-GX | RAID log – maintained and escalated | Paul Murray | Ongoing |  | RAID log – maintained and escalated
P-GX | 30 / 60 / 90 day reviews with business owner (from kick-off) | Paul Murray | Re-based | [7 empty] | 30 / 60 / 90 day reviews
AWS | AWS — AWS Tenancy Project (external dependency: Arinco / M-POWER)
AWS | AWS project contact and interface point confirmed | Paul Murray | Not started | [5 empty] | ◆ Contact
AWS | Requirements fed to AWS project — CIDR ranges, connectivity needs, timing | Bikramjit Saha | Not started | [5 empty] | Requirements to AWS project
AWS | Network architecture and connectivity pattern confirmed | AWS Tenancy Project | Due this month | [5 empty] | ◆ Pattern confirmed
AWS | AWS landing zone build (Transit Gateway, VPC/subnets, routing) — AWS project scope | AWS Tenancy Project / Arinco | External | [6 empty] | Landing zone build (AWS project)
AWS | Enterprise VPN / Transit Gateway operational (non-prod) | AWS Tenancy Project | External | [9 empty] | ◆ Non-prod connection
AWS | Enterprise connection production-ready (D24) | AWS Tenancy Project | External | [11 empty] | ◆ Prod connection (mid-Mar)
WP1 | WP1 — Platform Enablement
WP1 | Platform solution architecture design | Bikramjit Saha | Complete – confirm |  |  | Platform solution architecture design
WP1 | ARC and DRC approval (confirm body) | Bikramjit Saha | Complete – confirm |  |  |  |  | ◆ DRC approval
WP1 | Security approval — internet-based connectivity for dev/test (CRITICAL) | Petra Claessens / Paul Murray | Not started | [5 empty] | Security approval (internet dev/test)
WP1 | Interim internet connectivity live | TBC — assign | Not started | [6 empty] | ◆ Internet live
WP1 | MuleSoft licence keys applied to Anypoint organisation | Paul Murray | Planned | [6 empty] | ◆ Licence keys
WP1 | Private Space provisioning (internet-based; reserved CIDR — R9) | Bharat Patel | Planned | [6 empty] | Private Space (Wk 3–4)
WP1 | Set ingress rules for Azure developer subnets | Kunda Reddy | Planned | [6 empty] | Ingress rules
WP1 | Set up non-prod environments | Bharat Patel | Planned | [6 empty] | Set up non-prod environments
WP1 | Entra ID SSO — SAML design, Entra-to-Mule RBAC mapping, developer SSO | Bharat Patel | Planned | [6 empty] | Entra ID SSO / RBAC
WP1 | Security — Azure Key Vault secrets management | Bharat Patel | Planned | [7 empty] | Key Vault
WP1 | Log forwarding to SIEM | Bharat Patel | Planned | [7 empty] | SIEM
WP1 | Observability — monitoring and alerting | Bharat Patel | Planned | [7 empty] | Observability
WP1 | CI/CD pipelines — GitHub Actions, YAML; SAST/SCA via GitHub Advanced Security (D10) | Bharat Patel | Planned | [7 empty] | CI/CD pipelines
WP1 | Platform ready (non-prod) — Anchor | Bharat Patel | Planned | [7 empty] | ◆ Platform ready
WP1 | Buffer — environment provisioning and security approvals (+4 wks → Likely Dec 26) | — | Reference class | [8 empty] | Buffer +4 wks
WP1 | One-click deployment to dev | Bharat Patel | Planned | [9 empty] | ◆ Dev deploy
WP1 | Configure Azure VNet gateway and Anypoint VPN over enterprise connection | Kunda Reddy | Planned | [9 empty] | VNet gateway / Anypoint VPN
WP1 | IPsec tunnel verified active between clouds | Kunda Reddy | Planned | [10 empty] | ◆ Tunnel verified
WP1 | Migrate Private Space connectivity from internet to enterprise connection (non-prod) | Bharat Patel | Planned | [10 empty] | Migrate to enterprise connection
WP1 | Pen test — network tunnel and sample APIs | Petra Claessens / Deloitte | Planned | [10 empty] | Pen test
WP1 | Security approval — production deployment (R20) | Petra Claessens | Not started | [10 empty] | Prod security approval
WP1 | Production environment build over enterprise connection | Bharat Patel | Planned | [11 empty] | Prod build
WP1 | Ongoing platform hypercare and support | Deloitte | Planned | [7 empty] | Ongoing platform hypercare and support
WP2 | WP2 — Integration Intake, Discovery and Build (aligned to DCP)
WP2 | Integration register established (registration-first) — Jira intake | Paul Murray | Complete – Jira fields open | Integration register established
WP2 | Weekly planning and triage cadence | Paul Murray | Starting | [5 empty] | Weekly triage
WP2 | Intake discovery process defined — DCP-aligned criteria, registration-first, DRC sign-off | Paul Murray / Bharat Patel | Not started | [5 empty] | Intake discovery process
WP2 | DCP-aligned integration roadmap — from Claims Platform discovery and EA release 1 view (R22) | Bharat Patel / Joshua Ly | Not started | [6 empty] | DCP-aligned integration roadmap
WP2 | Intake funnel — discovery of new integration requests from DCP and transformation projects | Anu Verma | Ongoing | [7 empty] | Intake funnel (DCP and transformation projects)
WP2 | Priority 1 domain: Documents (EIM / SharePoint, Squiz) — discovery | Anu Verma | In progress |  |  | P1 Documents — discovery
WP2 | Priority 1 domain: Documents — build and test | Deloitte / TAC squad | Planned | [7 empty] | P1 Documents — build
WP2 | Priority 2 domain: External parties (health providers / eHealth, legal, employers) — discovery | Anu Verma | In progress |  |  | P2 External parties — discovery
WP2 | Decision gate: eHealth agrees push-to-pull change, or alternative solution adopted | Anu Verma | Open | [6 empty] | ◈ eHealth decision
WP2 | Priority 2 domain: External parties — build and test | Deloitte / TAC squad | Planned | [8 empty] | P2 External parties — build
WP2 | Priority 3 domain: Payments / Finance (Westpac, 13CABS, Ambulance Victoria) — discovery | Anu Verma | Blocked pending decision | [5 empty] | P3 Payments — discovery
WP2 | Decision gate: payment source of truth — Avanti vs Claims Platform (post Claims Platform discovery) | Joshua Ly | Open | [7 empty] | ◈ Payments decision
WP2 | Finance agreement — two-bank-account approach and reconciliation model | Anu Verma / Finance | Not started | [7 empty] | Finance agreement
WP2 | Priority 3 domain: Payments — build and test | Deloitte / TAC squad | Planned | [9 empty] | P3 Payments — build
WP2 | Integration frameworks and API design patterns established | Deloitte | Planned | [7 empty] | Frameworks and design patterns
WP2 | Core Claims domain (Avanti — anti-corruption layer, R12) | Deloitte | Planned | [8 empty] | Core Claims (Avanti)
WP2 | Customer / client data domain (CRM, client portal) | Deloitte | Planned | [9 empty] | Customer / client data
WP2 | Reporting / analytics-ready flows (Cathal Laffan, data governance forum) | Deloitte | Planned | [5 empty] | Analytics-ready flows
WP2 | Priority 1 integration build complete — Anchor | Paul Murray | Planned | [10 empty] | ◆ P1 build complete
WP2 | Buffer — legacy interface discovery (+4 wks → Likely Mar 27) | — | Reference class | [11 empty] | Buffer +4 wks
WP2 | Code complete / ready for production | Paul Murray | Planned | [11 empty] | ◆ Code complete
WP2 | Production deployment and hardening | Deloitte / TAC squad | Planned | [12 empty] | Prod deployment
WP2 | Ready for Claims Platform SIT — Anchor end Apr 27 (Likely May 27, Safe Jun 27) | Paul Murray | Planned | [12 empty] | ◈ READY FOR CLAIMS SIT
WP2 | Buffer — cascading allowance (Likely plan) | — | Reference class | [13 empty] | Buffer (Likely)
WP2 | Priority 2–4 go-live (TBC) | Paul Murray | TBC | [13 empty] | ◈ P2–4 go-live
WP2 | Staggered hypercare per use-case | Deloitte → TAC | Planned | [10 empty] | Staggered hypercare
WP2 | Ongoing integration catalogue refinement | TAC squad | Ongoing |  |  |  |  | Catalogue refinement
WP2 | OUT OF SCOPE — legacy IBM integrations run as-is under extended support (other area, D29) until Avanti retires | Other area — TBC | Out of scope | [5 empty] | Legacy IBM integrations — out of scope (D29)
WP2 | DCP Release 1 — Claims Platform programme (highly optimistic) | Joshua Ly | External | [19 empty] | ◆ DCP R1
WP3 | WP3 — People and Capability Enablement
WP3 | Capability uplift plan agreed | Paul Murray | Re-based | [6 empty] | ◆ Plan agreed
WP3 | TAC staff embedded in Deloitte squads (pairing and shadowing) | Deloitte | Planned | [6 empty] | Embedded in squads
WP3 | MuleSoft bootcamp and certification enablement | Deloitte | Planned | [6 empty] | Bootcamp and certification
WP3 | Progressive knowledge transfer (Show Me / Help Me / Let Me) | Deloitte | Planned | [7 empty] | Show Me / Help Me / Let Me
WP3 | Lunch and Learn / DRC sessions — monthly | Deloitte | Planned | [6 empty] | Monthly
WP3 | Integration design patterns and reusable API library | Deloitte | Planned | [7 empty] | Reusable API library
WP3 | Security and compliance architecture documentation | Deloitte | Planned | [7 empty] | Security architecture docs
WP3 | Interim data stewardship model for dual-platform period (I5, I6) | Cathal Laffan / Paul Murray | Not started | [6 empty] | Interim data stewardship model
WP3 | Data governance – definitions, quality rules, analytics-ready flows | Paul Murray | Planned | [7 empty] | Data governance
WP3 | Capability transfer complete — TAC squad at "Let Me" (Deloitte exit gate) | Paul Murray | HARD | [12 empty] | ◆ CAPABILITY TRANSFER
WP4 | WP4 — Operating Model and BAU Transition
WP4 | BAU / operations owner confirmed post-Deloitte (likely Bart Fine) | Paul Murray | Not started | [6 empty] | ◆ BAU owner
WP4 | Transition-in planning and operations handbook | Paul Murray | Planned | [7 empty] | Ops handbook
WP4 | Support model and incident management process defined | Paul Murray | Planned | [9 empty] | Support model
WP4 | API lifecycle management process established | Paul Murray | Planned | [10 empty] | API lifecycle
WP4 | RACI – integrated support model defined | Paul Murray | Planned | [10 empty] | RACI
WP4 | Managed services option decision (Bronze / Silver / Gold) — before Deloitte exit | Bart Fine | Not started | [10 empty] | ◈ Managed services decision
WP4 | Runbooks and documentation completed | Deloitte | Planned | [10 empty] | Runbooks
WP4 | Service Delivery Acceptance Test | Paul Murray | Planned | [11 empty] | ◈ SDAT
WP4 | Support transition to TAC BAU / nominated vendor | Paul Murray | Planned | [11 empty] | Support transition
WP4 | Deloitte exit | Paul Murray | HARD | [12 empty] | ◆ DELOITTE EXIT

## Milestones
Milestone register — Anchor / Likely / Safe (v2.1, 7 Sep 2026)
WP | Milestone | Type | A – Anchor | B – Likely | C – Safe | Owner | Depends on | Status
M-POWER | Domain name cutover | External | Sep 26 | Sep 26 | Oct 26 | Neil Carroll | M-POWER programme | Due this month
M-POWER | M-POWER production cutover | External | Oct 26 | Oct 26 | Nov 26 | Neil Carroll | M-POWER programme | Planned
P-GX | Deloitte contract executed | Internal | Sep 26 | Sep 26 | Oct 26 | Paul Murray | CEO submission (I9); Legal clause 4(f); AC.1 offshoring | At risk
P-GX | MuleSoft licence procured | Internal | Sep 26 | Oct 26 | Oct 26 | Trish Volante / Ankur Pawaria | Procurement (R16) | At risk
P-GX | Change Request approved ($290K) | Internal | Sep 26 | Oct 26 | Oct 26 | Paul Murray | Jennifer Rebeiro, Nick Popovski, Adam Roberts, Jordie Clark | In flight
P-GX | Project kick-off | Internal | Oct 26 | Oct 26 | Nov 26 | Paul Murray | Contract executed | Planned
AWS | Network architecture and connectivity pattern confirmed | External | Sep 26 | Oct 26 | Oct 26 | AWS Tenancy Project | Arinco engagement; requirements from Bikramjit | Due this month
WP1 | Security approval — internet-based dev/test | Internal | Oct 26 | Oct 26 | Nov 26 | Petra Claessens | Security review of interim approach | Not started
WP1 | Interim internet connectivity live | Internal | Oct 26 | Oct 26 | Nov 26 | TBC | Security approval; owner assigned | Not started
WP1 | Platform ready (non-prod) | Internal | Nov 26 | Dec 26 | Jan 27 | Bharat Patel | Internet connectivity; licence keys; M-POWER GO | Planned
AWS | Enterprise VPN / Transit Gateway operational (non-prod) | External | Jan 27 | Feb 27 | Feb 27 | AWS Tenancy Project | Landing zone build | External
WP1 | One-click deployment to dev | Internal | Jan 27 | Jan 27 | Feb 27 | Bharat Patel | CI/CD pipelines | Planned
WP2 | Priority 1 integration build complete | Internal | Feb 27 | Mar 27 | Apr 27 | Paul Murray | Platform ready; eHealth decision; discovery complete | Planned
AWS | Enterprise connection production-ready | External | Mid-Mar 27 | Late Mar 27 | Apr 27 | AWS Tenancy Project | D24 | External
WP1 | Production security approval | Internal | Mar 27 | Mar 27 | Apr 27 | Petra Claessens | Pen test; enterprise connection | Not started
WP2 | Code complete / ready for production | Internal | Mar 27 | Apr 27 | May 27 | Paul Murray | P1 build; enterprise connection | Planned
WP4 | Service Delivery Acceptance Test | Internal | Mar 27 | Apr 27 | Apr 27 | Paul Murray | Runbooks; support model | Planned
WP2 | Ready for Claims Platform SIT | Internal | End Apr 27 | End May 27 | End Jun 27 | Paul Murray | Prod deployment; prod security approval | Planned — confirm SIT date with Joshua Ly
WP3 | Capability transfer complete | HARD | Apr 27 | Apr 27 | Apr 27 | Paul Murray | WP3 stream | Planned
WP4 | Deloitte exit | HARD | Apr 27 | Apr 27 | Apr 27 | Paul Murray | Contract term — confirm exact date | Fixed
WP2 | Priority 2–4 go-live | Internal | May 27 | Jun 27 | Jul 27 | Paul Murray | Payments decision; P2/P3 build | TBC
WP2 | Intake discovery process defined | Internal | Oct 26 | Oct 26 | Nov 26 | Paul Murray | DRC agreement on DCP-aligned criteria | Not started
WP2 | DCP-aligned integration roadmap agreed | Internal | Dec 26 | Jan 27 | Feb 27 | Bharat Patel | Claims Platform discovery; EA release 1 view | Not started
WP2 | IBM end of life — extended support in place | External | Sep 27 | — | — | Other area — TBC | Not Digital Toolkit scope (D29) | Informational
WP2 | DCP Release 1 | External | Nov 27 | — | — | Joshua Ly | Claims Platform programme | Highly optimistic
Shading: red = hard date (does not move); orange = external dependency (tracked, not controlled).

## RAID Log
RAID Log v2.1 — carried forward from Keel extract 4 Sep 2026, with additions
REF | TYPE | DESCRIPTION | LIKELIHOOD | IMPACT | MITIGATION | OWNER | STATUS | RAISED
RISKS
R22 | Risk | Bart is feeling schedule pressure. Bharat will be 50:50 across Digital Toolkit and Claims. They will want to integrate the integration schedule with Claims delivery. Enterprise architecture will clarify integrations for release 1. | medium | high | Re-baseline plan against Claims Platform schedule at kick-off (Oct 26). Protect Bharat's Digital Toolkit allocation through platform enablement (Oct–Dec 26) as a named assumption (A7). Weekly triage is the shared forum with Claims Platform. | Paul Murray | open | 2026-09-04
R19 | Risk | AWS enterprise connection delivers late March, leaving less than 2 weeks for production deployment before April go-live | medium | high | Treat mid-March as the planning assumption; build dev/test on internet-based connectivity so only production is exposed to the AWS date. Escalate to AWS Tenancy Project at first sign of slip. Likely plan carries this to May 27. | Paul Murray | open | 2026-09-04
R20 | Risk | Security approval for production deployment could delay April go-live if not addressed early | medium | high | Open the production security conversation with Petra Claessens in Q4 26; agree the approval approach and evidence required before pen test (Feb 27) so approval is a formality, not a review. | Paul Murray | open | 2026-09-04
R21 | Risk | Internet connectivity setup (interim) could be delayed, blocking platform enablement and build work | medium | high | Confirm owner and target date this week; security approval for internet-based dev/test is the first critical-path item. If not approved by mid-Oct 26, platform ready moves to Dec 26 (Likely plan). | Paul Murray | open | 2026-09-04
R18 | Risk | That we shouldn't be trying to fast track AWS work to bring on MuleSoft | medium | medium | Resolved by design: AWS landing zone is no longer on the Digital Toolkit critical path for dev/test. Interim internet-based Private Space decouples MuleSoft enablement from AWS timing. | Paul Murray | open | 2026-09-04
R1 | Risk | Large amount of work in parallel | high | medium | Consider higher work in progress limits |  | open | 2026-09-04
R15 | Risk | Networking will take time, and with the M-POWER change, there is concern about building MuleSoft on unsteady ground. WorkSafe experienced 6 month delay when MuleSoft moved from CloudHub 1.0 to 2.0 — keen to learn from their difficulties. | low | high | Networking in play and part of the platform enablement work with help from TAC networking specialists to improve its readiness. Action: reference call with WorkSafe MuleSoft lead. | Paul Murray | open | 2026-09-04
R16 | Risk | The purchasing of MuleSoft licence, if slow, will really impact timelines | high | medium | There is buffer in our timeline to allow for a potential delay. Licence keys needed by Oct 26 for Private Space provisioning. | Trish Volante | open | 2026-09-04
R13 | Risk | Dual system costs are rarely temporary — the legacy system never fully decommissions. TAC ends up running Avanti and the new Claims platform indefinitely. | high | high | Define explicit decommission criteria and date before programme starts. Make decommission a programme milestone, not a post-programme activity. Governance to hold the line. Note: IBM extended support past Sep 27 (D29) is the first instance of this risk materialising — outside this programme's scope. | Jennifer Rebeiro | open | 2026-09-04
R12 | Risk | Architectural debt becomes permanent — every compromise made to keep the legacy system running while building the new one gets baked into the new system's design. Conway's Law — you ship your architecture. | high | high | Foundational platform delivery — establish clean architecture before integration with legacy. Define and enforce Anti-Corruption Layer between new platform and Avanti. DRC to govern. | Sarah Kremar | open | 2026-09-04
R9 | Risk | CIDR overlap — immutability: once a Private Space is built with a specific CIDR block it cannot be changed. Discovering overlap in pre-prod means deleting the environment and starting again. | low | high | Network team to reserve a unique, non-overlapping CIDR block for the MuleSoft VPC before the interim Private Space is provisioned (Oct 26), so the internet-based Private Space can migrate to the enterprise connection without rebuild. | M-POWER / Bikramjit Saha | open | 2026-09-04
R6 | Risk | Avanti feature changes would impact the accuracy of the requirements and build of the new platform. Moving goal posts. | high | medium | Anti-corruption layer (R12) limits blast radius. Register Avanti change requests through weekly triage so impacts are visible. |  | open | 2026-09-04
R23 | Risk | Payment source-of-truth decision (Avanti vs Claims Platform) is not made until after Claims Platform discovery. Priority 3 Payments build cannot start, and P2–4 go-live slips. | high | high | Decision owner Joshua Ly. Confirm decision timing at kick-off; plan assumes Nov 26. Run Payments discovery (Westpac, 13CABS, Ambulance Victoria flows) in parallel so build is ready to start the day the decision lands. | Joshua Ly | open | 2026-09-04
R24 | Risk | eHealth does not agree to change from push to pull, requiring an alternative solution for the external parties domain. | medium | medium | Raise the request formally in Sep 26; define the alternative pattern now so the Oct 26 decision gate has two viable options. | Anu Verma | open | 2026-09-04
R25 | Risk | Two-bank-account approach creates a reconciliation load the Finance team has not agreed to; Finance and Westpac business team engagement is heavy and slow. | medium | high | Anu Verma to lead engagement; agree approach with Finance by Dec 26. Escalate through Bart Fine if Finance capacity is not confirmed. | Anu Verma | open | 2026-09-04
R26 | Risk | Reference class: legacy interface discovery on Avanti, eHealth and Westpac is more complex than documented (typical slip 3–8 weeks). | high | medium | Explicit +4 week buffer after P1 build complete (Likely plan). Present ranges, not points, to stakeholders. | Paul Murray | open | 2026-09-04
R27 | Risk | Pressure to use the MuleSoft platform to migrate legacy IBM integrations (because of the Sep 27 end of life) pulls the squad off DCP-aligned build. This is not a strategic direction — most legacy integrations will not exist in the new world. | medium | high | Scope boundary written into the plan and business case. Intake discovery process is the gate: legacy requests only enter via a transformation project that owns them. Escalate to Bart Fine if pushed. | Paul Murray | open | 2026-09-07
R28 | Risk | DCP Release 1 (Nov 27) slips or its integration needs are not defined in time, so the intake funnel has no reliable demand signal and the squad builds the wrong things or waits. | high | high | DCP-aligned roadmap from Claims Platform discovery (Oct–Dec 26) is the demand signal; weekly triage with Joshua Ly keeps it current. Interim data stewardship model (WP3) designed for an open-ended dual-platform period. | Jennifer Rebeiro | open | 2026-09-07
R3 | Risk | Based on previous conversations James Thomas had, there is a chance Petra Claessens has forgotten the security review she already completed | medium | medium |  |  | closed | 2026-09-04
ASSUMPTIONS
A1 | Assumption | Deloitte eServices contract is executed by end Sep 26 and the squad is mobilised by mid-Oct 26. |  |  | If not: kick-off and every downstream milestone slip week-for-week. | Paul Murray | open | 2026-09-04
A2 | Assumption | IT Security approves internet-based connectivity for dev/test, and it is available by Oct 26. |  |  | If not: platform ready moves to Jan 27 (Safe plan) and dev/test waits on the AWS enterprise connection. | Petra Claessens | open | 2026-09-04
A3 | Assumption | AWS Tenancy Project delivers the enterprise connection non-prod in Jan 27 and production-ready by mid-Mar 27. |  |  | If not: production deployment slips; Ready for Claims SIT moves to May/Jun 27. | AWS Tenancy Project | open | 2026-09-04
A4 | Assumption | A Private Space built on internet connectivity can migrate to the enterprise connection without rebuild, because the CIDR block is reserved up front. |  |  | If not: environment rebuild in Feb 27 (R9). | Bikramjit Saha | open | 2026-09-04
A5 | Assumption | Avanti, eHealth and Westpac interfaces behave as documented; undocumented complexity is absorbed by the 4-week buffer. |  |  | If not: P1 build complete moves beyond Mar 27. | Anu Verma | open | 2026-09-04
A6 | Assumption | Claims Platform SIT starts end Apr 27. |  |  | Confirm with Joshua Ly. If SIT is later, the Likely plan may be sufficient without escalation. | Joshua Ly | open | 2026-09-04
A7 | Assumption | Bharat Patel is at least 50% allocated to Digital Toolkit through platform enablement (Oct–Dec 26). |  |  | If not: platform ready slips; no substitute for platform tech lead. | Bart Fine | open | 2026-09-04
A8 | Assumption | MuleSoft licence is procured and keys are available by Oct 26. |  |  | If not: Private Space provisioning waits (R16). | Trish Volante | open | 2026-09-04
A9 | Assumption | Deloitte exit in Apr 27 is fixed; no extension will be sought. Production deployment under Likely/Safe plans is completed by the TAC squad. |  |  | Confirm exact contractual date. | Paul Murray | open | 2026-09-04
A10 | Assumption | Legacy IBM integrations are out of scope. IBM continues to run Avanti past its Sep 27 end of life under an extended-support arrangement owned by another area; this programme builds new integrations for DCP needs only. |  |  | If challenged: scope change with cost and schedule impact — goes through the CR process. The Sep 26 M-POWER environment commitment is treated as superseded — confirm with Jennifer Rebeiro. | Jennifer Rebeiro | open | 2026-09-07
A11 | Assumption | Payment source-of-truth decision lands by Nov 26 following Claims Platform discovery. |  |  | If not: P3 Payments build and P2–4 go-live slip (R23). | Joshua Ly | open | 2026-09-04
A12 | Assumption | DCP Release 1 is Nov 27 (highly optimistic). The integration roadmap is derived from DCP needs; the platform and P1 integrations are ready well ahead of it. |  |  | If it slips, the intake funnel slows but nothing built is wasted (R28). | Joshua Ly | open | 2026-09-07
ISSUES
I11 | Issue | $340K was removed from Digital Toolkit for AWS seed funding phase but the correct amount should be $290K | medium |  | Correct through the formal Change Request in flight. | James Thomas | open | 2026-09-04
I10 | Issue | Anu Verma not getting much time from Shenanas for the Payments integration work | medium |  | Paul to confirm Anu as lead for Payments engagement and agree her allocation with Shenanas. | Shenanas | open | 2026-09-04
I9 | Issue | CEO contract submission blocked pending Deloitte contract. | high |  | eServices contract signed by Deloitte and ready for CEO to review | Paul Murray | open | 2026-09-04
I6 | Issue | No data stewardship function or ownership model currently exists at TAC (confirmed by Cathal Laffan). Live risk to the Integration project because data will coexist across the legacy IBM platform and MuleSoft CloudHub 2.0 during transition with no defined accountability for quality, lineage, access control or conflict resolution. | high |  | 1. Create awareness. 2. Nominate data stewards for each affected domain. 3. Agree an interim stewardship model covering the dual-platform transition — authoritative source of truth per domain, escalation path for conflicts. Added to WP3 as a named stream (Oct–Nov 26), designed for an open-ended transition. | Cathal Laffan | open | 2026-09-04
I5 | Issue | Data ownership is missing. Need to be clear on who owns what data especially while data could live in both old platform and new during interim state | high |  | Covered by I6 interim stewardship model. |  | open | 2026-09-04
I4 | Issue | Concern about not being able to lock down scope with Bart Fine and confusion around execution from project based to persistent teams. | medium |  | Plan re-baseline at kick-off (Oct 26) fixes P1–P3 scope; weekly triage governs additions. | Bart Fine | open | 2026-09-04
I3 | Issue | Currently 3–4 different methods for project engagement with different RACIs. Many different approaches is hurting delivery | high |  |  |  | open | 2026-09-04
I2 | Issue | The integration project is currently flagged as red status | high |  | Re-baselined plan with explicit ranges and assumptions is the path back to amber. |  | open | 2026-09-04
I1 | Issue | Diagram is needed but ownership is unclear — who will do it? | medium |  |  |  | open | 2026-09-04
I7 | Issue | We cannot proceed with MuleSoft on-premise connection; any on-prem connection to applications or Azure is pending until AWS figures out either the IPsec or transit gateway. | medium |  | Interim internet-based connectivity for dev/test decouples enablement from this. On-prem connectivity remains tied to AWS enterprise connection (D24). |  | open | 2026-09-04
I12 | Issue | Jira integration request ticket missing custom fields on the create screen; Integration Request defaulting as create type across all DT boards. Action was due 27 Aug — overdue. | medium |  | Fix before weekly triage starts using the register in anger. | Paul Murray | open | 2026-09-04
DEPENDENCIES
D29 | Dependency | IBM extended support / keep-lights-on beyond Sep 27 end of life — owned by another area of the business. Informational: no Digital Toolkit scope attaches to it; legacy IBM integrations are not being migrated. | inbound |  | Know the owner; note status in reporting so the scope boundary stays visible. | Other area — TBC | open | 2026-09-07
D24 | Dependency | External dependency on AWS project delivering enterprise connection (VPN/Transit Gateway) production-ready by mid-March 2027 to enable production deployment before April deadline | inbound |  |  | TBC — AWS project contact | open | 2026-09-04
D26 | Dependency | Payment source-of-truth decision (Avanti vs Claims Platform) from Claims Platform discovery — gates Priority 3 Payments build. | inbound |  |  | Joshua Ly | open | 2026-09-04
D27 | Dependency | eHealth agreement to change from push to pull — gates Priority 2 External parties build. | inbound |  |  | Anu Verma | open | 2026-09-04
D28 | Dependency | Finance team agreement to two-bank-account approach and reconciliation model; Westpac business team engagement. | inbound |  |  | Anu Verma / Finance | open | 2026-09-04
D25 | Dependency | Make sure there is an audit trail of everything that has happened | inbound |  |  |  | open | 2026-09-04
D23 | Dependency | The IBM contract and migration timeline is dependent on how long Avanti needs to keep running. | inbound |  | Superseded by D29. |  | open | 2026-09-04
D22 | Dependency | Once co-location and firewall are sorted out, these are the critical elements that can allow MuleSoft enablement and API build to move forward | inbound |  |  |  | open | 2026-09-04
D21 | Dependency | Bikramjit Saha to meet with Checkpoint as a firewall vendor | inbound |  |  | Bikramjit Saha | open | 2026-09-04
D18 | Dependency | CDMU integration needs — on radar, requires attention | inbound |  |  |  | open | 2026-09-04
D19 | Dependency | CDMU new migration strategy under consideration | inbound |  |  |  | open | 2026-09-04
D20 | Dependency | AWS timing — need to understand how long it will take and impact on programme | inbound |  | Superseded by the three tracked AWS milestones (Sep 26, Jan 27, mid-Mar 27). Close once AWS contact confirms. |  | open | 2026-09-04
D17 | Dependency | When is the seed funding going to be approved. Are the DXC people coming onboard. When can we move. Need an answer on when the people from Arinco will come onboard. | inbound |  |  | Christie Rentsch | open | 2026-09-04
D16 | Dependency | Need an answer on when the people from Arinco will come onboard. Related to seed funding approval, DXC people coming onboard, and when we can move. | inbound |  | Duplicate of D17 — merge. | Christie Rentsch | open | 2026-09-04
D14 | Dependency | Need to bridge the gap of the Deloitte contract for MuleSoft work | inbound |  |  |  | open | 2026-09-04
D15 | Dependency | Digital Toolkit pays for AWS seeding funding document. AWS will get its own money, independent of the current programme. | inbound |  |  |  | open | 2026-09-04
D13 | Dependency | DXC needs to make the network and connectivity happen | inbound |  |  | Christie Rentsch | open | 2026-09-04
D12 | Dependency | Azure VPN config depends on M-POWER production cutover | inbound |  |  | Andrew Flanagan | open | 2026-09-04
D11 | Dependency | Need a network landing zone for CloudHub 2.0 — secure private bridge between Azure VNet and MuleSoft VPC (in AWS). Requires IPsec VPN setup with Virtual Network Gateway in Azure. | inbound |  | Now AWS Tenancy Project scope. Duplicate of D2 — merge. |  | open | 2026-09-04
D9 | Dependency | MuleSoft to on-prem is with DXC, not M-POWER. Need to engage DXC using Time and Materials approach (other approaches are slow). Will cost project expenditure. | inbound |  |  | Andrew Flanagan | open | 2026-09-04
D10 | Dependency | GitHub is the repo of choice. SAST and DAST covered with GitHub Advanced, and GitHub Actions will be used for deployment steps | inbound |  |  |  | open | 2026-09-04
D8 | Dependency | No domain until September, so platform enablement work cannot proceed until domain name cutover happens | inbound |  |  |  | open | 2026-09-04
D5 | Dependency | Legal Matters Management is a potential integration coming up soon for the go-live of self-serve. | inbound |  |  |  | open | 2026-09-04
D6 | Dependency | Core Claims platform is a potential integration for the go-live of self-serve. | inbound |  |  |  | open | 2026-09-04
D7 | Dependency | EIM content management/document management in SharePoint is a potential early integration. | inbound |  |  |  | open | 2026-09-04
D2 | Dependency | Need a network landing zone to create a secure, private bridge between Azure VNet and the MuleSoft VPC in AWS | inbound |  | Now AWS Tenancy Project scope. |  | open | 2026-09-04
D3 | Dependency | SSO needs to be configured in the new tenancy for the Anypoint Platform | inbound |  |  |  | open | 2026-09-04
D4 | Dependency | MuleSoft integration will need access to Azure Service Bus and Azure Storage | inbound |  |  |  | open | 2026-09-04
D1 | Dependency | M-POWER Go-Live | outbound |  |  |  | open | 2026-09-04
Green REF = new or changed in v2/v2.1. Scope position corrected 7 Sep 2026: legacy IBM integrations out of scope (R27, R28, A10, A12, D29).

## Actions & Decisions
Immediate actions (next two weeks) and open decisions
# | ACTION | OWNER | DUE | STATUS | WHY IT MATTERS
1 | Confirm AWS Tenancy Project contact and interface point; agree the three tracked milestones (Sep 26 / Jan 27 / mid-Mar 27) | Paul Murray | 11 Sep 26 | Open | Unblocks D24 ownership and the whole AWS dependency line
2 | Confirm owner and target date for interim internet connectivity | Paul Murray | 11 Sep 26 | Open | First critical-path item (R21)
3 | Open security conversation with Petra Claessens on internet-based dev/test connectivity; request approval approach | Paul Murray | 11 Sep 26 | Open | Gate for Oct 26 platform work (A2)
4 | Feed CIDR, connectivity and timing requirements to AWS project; confirm reserved non-overlapping CIDR for MuleSoft VPC | Bikramjit Saha | 18 Sep 26 | Open | R9 and A4 — avoids Private Space rebuild
5 | Confirm Claims Platform SIT start date and payment source-of-truth decision timing | Paul Murray → Joshua Ly | 11 Sep 26 | Open | A6, A11 — anchors the whole plan
6 | Confirm Anu Verma as lead for Payments / Westpac engagement (Finance, Westpac business team) and agree allocation with Shenanas | Paul Murray / Bart Fine | 11 Sep 26 | Open | I10, R25
7 | Raise eHealth push-to-pull request formally; document the alternative pattern | Anu Verma | 30 Sep 26 | Open | R24 decision gate Oct 26
8 | Fix Jira Integration Request create screen (missing fields; wrong default type) | Paul Murray | Overdue (27 Aug) | Open | I12 — register must work before weekly triage
9 | Three reference calls: Deloitte proposed lead, MuleSoft account team (reference customer), Arinco (what delays enterprise VPN/Transit Gateway) | Paul Murray | 11 Sep 26 | Open | Reference-class data for buffers; 15 minutes each
10 | Confirm exact Deloitte exit date and whether an extension is contractually possible | Paul Murray | 11 Sep 26 | Open | A9 — hard date on the plan
11 | Identify the owner of the IBM extended-support work in the other area so the scope boundary is visible in reporting | Paul Murray | 18 Sep 26 | Open | D29 — informational only
12 | Define the intake discovery process — DCP-aligned acceptance criteria, registration-first, DRC sign-off — and agree it with Bart Fine and Joshua Ly | Paul Murray / Bharat Patel | Kick-off (Oct 26) | Open | The driving force of WP2; the gate that keeps legacy migration requests out
13 | Present plan as ranges: Anchor / Likely / Safe with named assumptions, to Bart Fine then Jennifer Rebeiro | Paul Murray | 18 Sep 26 | Open | Moves project from red to amber with a defensible baseline (I2)
Open decisions
# | DECISION | DECISION-MAKER | NEEDED BY | STATUS | CONTEXT
DEC1 | Where payments originate during transition — Avanti or Claims Platform (all payments route via Westpac; today all go through Avanti except Ambulance Victoria; 13CABS invoice flow needs full view) | Joshua Ly | Nov 26 | Open | From pre-triage 27 Aug. Comes out of Claims Platform discovery. Gates P3 Payments build.
DEC2 | Two-bank-account approach and reconciliation model acceptable to Finance | Finance (via Anu Verma) | Dec 26 | Open | Heavy reconciliation load on Finance; requires Westpac business team engagement.
DEC3 | eHealth push-to-pull change agreed, or alternative solution adopted | Anu Verma (with eHealth) | Oct 26 | Open | Gates P2 External parties build.
DEC4 | Internet-based connectivity for dev/test approved as interim pattern | Petra Claessens | Oct 26 | Open | Gates Oct 26 Private Space provisioning; decouples enablement from AWS timing.
DEC5 | Managed services option post-Deloitte (Bronze / Silver / Gold) or full TAC BAU | Bart Fine | Feb 27 | Open | Must land before Deloitte exit; drives WP4 transition scope.
DEC6 | Governance naming — is "ARC" a real approval body, or should the plan read DRC only | Paul Murray / Bharat Patel | 18 Sep 26 | Open | Consistency with position paper and exec pack (DRC, never ARB).
DEC7 | Intake acceptance criteria — what qualifies an integration request as DCP-aligned, and how legacy requests from other transformation projects are handled | DRC (Bharat Patel) with Bart Fine | Oct 26 | Open | Codifies the scope boundary: build for the new world, do not migrate IBM.

## Stakeholder Map
Stakeholder Map (carried forward — populate priority and engagement)
FUNCTIONAL AREA | ROLE | NAME | PRIORITY | ENGAGEMENT | INTEGRATION RELEVANCE | GAP / NOTES
Accountable | Business Owner | Bart Fine |  |  |  | Confirm as BAU owner post-Deloitte (WP4)
Accountable | Sponsor | Jennifer Rebeiro |  |  |  | CR approver; confirm A10
Accountable | Portfolio Manager | Tina Singh
Affected | Cyber Security | Paul Blowers |  |  |  | Petra Claessens holds security approvals in plan — confirm split
Affected | Claims Platform Programme Manager | Joshua Ly |  |  |  | Decision-maker DEC1; SIT date and DCP R1 owner
Affected | IBM extended support / keep-lights-on owner | TBC — other area |  |  |  | D29 — informational; identify (Action 11)
Affected | Finance | TBC |  |  |  | DEC2 — two-bank-account reconciliation
Active | Digital Delivery | Paul Bookless
Active | Procurement Lead | Ankur Pawaria |  |  |  | MuleSoft licence (R16)
Active | Legal Counsel | John Christianakis |  |  |  | Deloitte clause 4(f); AC.1 offshoring
Active | Integration analyst | Anu Verma |  |  |  | Leads P1–P3 discovery; Payments engagement
Active | AWS Tenancy Project contact | TBC |  |  |  | Action 1